## Sheet1
Item | Start Date | End Date
TODAY
Senior Project | 2018-01-22 | 2019-05-03
ECE 401/5 | 2018-01-22 | 2018-05-04
ECE 402/6 | 2018-09-04 | 2018-12-21
ECE 403 | 2019-01-22 | 2019-05-03
Item | Start Date | End Date | ECE 401 | Action Item | Document Name | Font
TODAY
ECE 401 | 2018-01-22 | 2018-05-04
Abstract | 2018-01-22 | 2018-02-14 |  | Please create a Google Teams document that contains your abstract. | Abstract | 12 pt Times New Roman
Abstract Revisions I | 2018-02-14 | 2018-02-26 |  | Revise Abstract based on comments
Specifications | 2018-02-14 | 2018-02-26 |  | Please create a Google Teams document that contains your specifications. The font size shall be 12 pt and the font shall be Times New Roman. | Specs | 12 pt Times New Roman
Abstract Revisions II Specifications Revision I | 2018-02-26 | 2018-03-05 |  | Revise Abstract and Specs based on comments
Feasibility | 2018-02-19 | 2018-03-05 |  | Please create/write/edit a Google Teams document that contains your feasibility. The font size shall be 12 pt and the font shall be Times New Roman. | Feasibility | 12 pt Times New Roman
Expense Report | 2018-03-05 | 2018-03-26 |  | Please create/write/edit a Google Teams sheet that contains your expense report. The font size shall be 10 pt and the font shall be Arial. | Expense Report | 10 pt Arial
Abstract Revisions III Specifications Revision II Feasiblity Revision I | 2018-03-05 | 2018-03-26 |  | Revise Abstract, Specs, & Feasibility based on comments
Contract | 2018-03-26 | 2018-04-11 |  | Please create/write/edit a Google Teams document that contains your contract. | Contract | 12 pt Times New Roman
Extended Feasibility | 2018-03-26 | 2018-04-11 |  | Please extended your Google Teams feasibiilty document.
Schedule | 2018-03-26 | 2018-04-11 |  | Please create/write/edit a Google Teams sheet that contains your project schedule. | Gannt Chart | 10 pt Arial
Final Revisions | 2018-04-11 | 2018-05-04 |  | Revise any and all documents based on comments
Proposal Package Due |  | 2018-05-04 |  | Proposal Package (Abstract, Extended Feasibility, Contract, Notebooks, Revision Control, Schedule, and Expense Report). Place notebooks in Sheaff's mailbox, 101 Barrows before the office closes.
Item | Start Date | End Date | ECE 402/406 | Action Item | Document Name | Font
TODAY
ECE 402/406 | 2018-09-04 | 2018-12-21
Microphone Testing | 2018-09-04 | 2018-09-06 |  | Test the microphone output
Power Supply Design | 2018-09-04 | 2018-09-13 |  | Design and test power supply, decide whether to use buck or boost converter
Amplify Microphone Output | 2018-09-06 | 2018-09-13 |  | Design operational amplifier with feedback network
Software design - Frequency Detection | 2018-09-06 | 2018-09-15 |  | Write codethat will use digital signal processing to detect fundamental frequency
Written Progress Report #1 | 2018-09-10 | 2018-09-20 |  | Written Progress report due | Written Progress Report #1 | 12 pt Times New Roman
Verification Report | 2018-09-10 | 2018-09-13 |  | Written Progress report due | Verification Report #1 | 12 pt Times New Roman
Parts Order #1 | 2018-09-18 | 2018-09-18 |  | Written Progress report due | Justification Report #1 | 12 pt Times New Roman
Analog Filter Design | 2018-09-11 | 2018-09-18 |  | Design analog filter that will filter unwanted harmonics
Up to date schedule & Verification | 2018-09-13 | 2018-09-20
Analog to Digital Conversion | 2018-09-18 | 2018-09-25 |  | Test selected analog to digital converter
Circuit Schematic Design | 2018-09-18 | 2018-10-01 |  | Revise and update circuit design schematic
Written Progress Report #2 | 2018-09-26 | 2018-10-04 |  | Written progress report #2 due | Written Progress Report #2 | 12 pt Times New Roman
Breadboard Prototyping | 2018-10-01 | 2018-10-03 |  | Build prototype circuit on breadboard, test the output, analyze data, comparing to contract specifications
Design PCB | 2018-10-01 | 2018-10-03 |  | Design and submit PCB for ordering
LCD Software and finalizing software for frequency detection | 2018-10-02 | 2018-10-18 |  | Write software to communicate with LCD, writing frequency to display
PCB Order #1 | 2018-10-03 | 2018-10-03 |  | Written Progress report due | Justification Report #2 | 12 pt Times New Roman
Construct circuit | 2018-10-18 | 2018-11-12
Oral Progress Reports | 2018-10-23 | 2018-11-01 |  | Oral progress report meeting time
PCB Order #2 | 2018-10-29 | 2018-10-29 |  | Written Progress report due | Justification Report #3 | 12 pt Times New Roman
Qualifies Week | 2018-11-05 | 2018-11-09
Design Review | 2018-12-17 | 2018-12-21
Total Percent Complete | 2018-09-04 | 2018-12-21 | 100%
Item | Start Date | End Date | ECE 402/406 | Action Item | Document Name | Font
TODAY
ECE 403 | 2019-01-22 | 2019-05-03
Written Report: First Round | 2019-01-22 | 2019-02-20 |  | Written report #1 due | Written report #1 | 12 pt Times New Roman
Written Report: Polished | 2019-02-28 | 2019-03-20 |  | Written Report : Polished due | Polished Report | 12 pt Times New Roman
Presentation:Specifications and Execution | 2019-03-13 | 2019-05-01 |  | Work on presentations, prepare for day of presentation
Final Package | 2019-05-03 |  |  | Senior capstone report due date | Capstone Report | 12 pt Times New Roman
Formulas:
Start Date = [Start Date, row above]
End Date = [End Date, row below]